## Checklist
[Company Name]
TRANSITION PLANNING CHECKLIST FOR PART 820 RESIDENTIAL IMPLEMENTATION
Activity | Owner | Time frame for completion | Actual Completion Date
PROGRAM DESIGN AND APPLICATION TASKS AND REVIEW
Develop a trans disciplinary change team utilizing subject matter experts to include (Clinical, IT, Finance, Facilities, Human Resources, etc.) that will be utilized to plan, development and implement the transition to Part 820.
Deliver overall vision to the staff and community stakeholders for input and revision.
Conduct self-assessment and identify which elements of care will support agency mission.
Engage Leadership and Board support to assign and prioritze resources throughout for changes in new service and financial model.
Identify EBP curriculums and a menu of services to be provided within each element of care.
Identify Measurement Based Care tools to be utilized for person-centered assessment and treatment planning.
Create a training plan for trans disciplinary team members to implement assessment tools and EBP's.
Identify new staff and recovery peer advocates
Redefine supervision to support element of care
Complete assessment of space needs based on service level, staffing needs and service activities
Applicants for the Element of Stabilization will collaborate with the Medical Director to develop an Ancillary Withdrawal Protocol
Revise agency and program policies and procedures to be in alignment with Part 820 and its clinical underpinnings.
Submit completed application to credentialing.
Develop budget and VAP request in collaboration with the Field Office.
Initate contract discussions with MCOs for new service elements
Engage vendor to discuss EMR/ EHR updates to reflect Part 820 transition (I.e. PAS forms, data collection, measurement based care tools, utilization review documentation)
Receive designation for Part 820
IMPLEMENTATION - BILLING: Rate / CPT / HCPSC codes; NYS MMIS Numbers; National Provider Identification Numbers
Review Mananged care billing manual for element specific : rate codes; CPT /HCPS and modifiers. https://www.omh.ny.gov/omhweb/bho/harp-mainstream-billing-manual.pdf. ALL BILLING for Medicaid recipients is via contract with plans. There is no Medicaid FFS billing.
NYS MMIS # (necessary to contract with plans to service medicaid enrollees). Program must determine if it will: utilize existing MMIS # ; request a new MMIS #; or if never enrolled in Medicaid will need a MMIS number. If program wants a new MMIS # or needs to enroll in NYS Medicaid program must complete / submit Part 820 specific Medicaid Enrollment Packet https://www.emedny.org/info/ProviderEnrollment/OASAS/index.aspx
National Provider Identificaiton Numbers (NPS)NYS does not issue NPIS . Programs should review the following link for additional information on Program vs Individual provider NPI. “For Information on how to obtain an NPI # please see : https://nppes.cms.hhs.gov/NPPES/Welcome.do” Plans will require the program NPI to configure in the system; and, when sumbitting the per diem claim the attending provider ID field will need an individual's NPI . Configuration in a plans claiming structure will vary by plan so programs will want to meet with plans discuss.
Designate NPI# within PRU for billing
Initate application process to obtain NPI numbers for all qualified staff
Ensure prcocess is in place to: affirm enrolless plan. Or for service recipients enrolled after admission indentify date of enrollment. Claims submission to plan commensurate to plan enrollment. Programs may not submit claims to Medicaid FFs.
Contact local DSS to identify transition to Part 820 designation and eligibility for Congregate Care Level II. Conduct education transfer surrounding mandated LOCADTR 3.0
Provide new Program Identification information to OASAS Finance/Billing Unit for set up of billing capability for new 820 services with OASAS
Upon implementation trouble shoot contractual issues, billing issues, appeals for length of stay, etc.
IMPLEMENTATION - MCO
Invite MCO for walk through to illustrate Part 820 elements of care service provisions.
Disccuss with MCOS the: state and MCO specific requirements for each MCO for billing system specification (eg. Rate / HCPC / CPT codes; NPI program number each MCO requires, program vs. parent organization; discuss test claiming.
Discuss contracting including; process to be fully configured in network and claims systems.
Confirm all qualified staff have NPI numbers .
Work through test run of billing process with individual MCO's
Identify Contact Person for individual MCO's - Director of Behavioral Health Services
Establish relationship with Supervisor of Case Managers in each MCO
Request assignment of specific case managers for your PRU
Stage transition of particpants to new elements of care utilizing LOCADTR being mindful that concurrent reviews will take place on the 14th day.
Explore with MCO expectations for documentation and concurrent/continuing care review
Develop protocols for staffing, management and tracking of Managed Care Notification and Concurrent Reviews with Managed care
Train staff on completion of concurrent review forms and management of appeals
IMPLEMENTATION - IT AND EMR
Identify new service elements and required additions to EHR including medical, psychiatric services
Provide input to EHR Vendor on needed elements, data fields, forms, outcomes, timeframes and reports for new service areas
Prepare for integration of new PAS Forms in EMR and do testing if applicable
Roll out new screening tools, forms and documentation expectations and requirements in EHR
Conduct testing with vendor to assure EHR reflects new billing and documentation requirements
Plan for HCS accounts, LOCADTR, HERDs and e-finds transfer. Dialogue with OASAS for the transition of accounts.
IMPLEMENTATION- OUTREACH AND COMMUNITY PREPARATION
Access Medicaid Managed Care Plan Enrollers
Share Part 820 program changes to key stakeholders
Speak to Local Referral Sources surrounding need for participant enrollment in a Managed Care plan
Have marketing tools in place
Identify potential changes to referral flow as a result of the revised design and shorter lengths of stay
Expand community linkages if needed including Health Homes and Recovery Oriented Community supports.
IMPLEMENTATION - WORKFORCE DEVELOPMENT
Roll out new screening tools, forms and documentation expectations and requirements with staff (i.e. measurement based care tools, treatment planning, progress note documentation, PAS forms and data collection tools, etc.)
Hire and recruit staff for key positions to be added to support the Part 820 service design (i.e., MD, Psychiatrist, PNP, RN, LPN, Social Worker, Peer Recovery Advocate)
Complete enrollment for new medical providers on EHR, E-Scribe, liability, etc.
Enroll staff in HCS system for LOCADTR if not already completed
Identify protocols for internal communication of new service elements and workflow issues.
IMPLEMENTATION- OPERATIONAL PREPARATION
Having confirmed and tested that internal and external processes are live prepare LOCADTR's for current participants in a staged format.
Revise Pharmacy MOU and identify needs/plan to ensure MAT and ancillary withdrawal needs are met
Share imminent program changes with existing participants prior to transition to Part 820.
Access all potentially needed CDS reports from previous 819 or 816.9 PRU prior to transition to new Part 820 designation.
IMPLEMENTATION - FACILITIES
Complete renovations of space required for repurposing or minor renovations
Complete inventory and purchases of furniture or equipment needed for additional staff (I.e. medical equipment, computers, phones, etc.)
Reconfigure participant space and staff offices as needed to accommodate Part 820 elements of care and services.